## Octorber
Project timeline
Date of Start : | 2020-10-01
| Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 5
| oct | [6 empty] | oct | [6 empty] | oct | [6 empty] | oct
Date | 2020-10-01 | 2020-10-02 | 2020-10-03 | 2020-10-04 | 2020-10-05 | 2020-10-06 | 2020-10-07 | 2020-10-08 | 2020-10-09 | 2020-10-10 | 2020-10-11 | 2020-10-12 | 2020-10-13 | 2020-10-14 | 2020-10-15 | 2020-10-16 | 2020-10-17 | 2020-10-18 | 2020-10-19 | 2020-10-20 | 2020-10-21 | 2020-10-22 | 2020-10-23 | 2020-10-24 | 2020-10-25 | 2020-10-26 | 2020-10-27 | 2020-10-28
Get the background infromation | 2020-10-01: Get the background infromation
gettering relevent informaion | 2020-10-05: gettering relevent informaion
Login / Log out Page Design | 2020-10-08: Login / Log out Page Design
Research Google Map Api | 2020-10-08: Research Google Map Api
#1 Moduel: `Shelters` Design | 2020-10-11: First Moduel: `Shelters` Design
#2 Modeul: 'BC Housing' Design | 2020-10-17: Second Modeul: 'BC Housing' Design
#3 Moduel: 'Hospitals' Design | 2020-10-23: #3 Moduel: 'Hospitals' Design

## November
Project timeline
Date of Start : | 2020-10-29
| Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 5
| oct |  |  | nov |  |  |  | nov | [6 empty] | nov | [6 empty] | nov
Date | 2020-10-29 | 2020-10-30 | 2020-10-31 | 2020-11-01 | 2020-11-02 | 2020-11-03 | 2020-11-04 | 2020-11-05 | 2020-11-06 | 2020-11-07 | 2020-11-08 | 2020-11-09 | 2020-11-10 | 2020-11-11 | 2020-11-12 | 2020-11-13 | 2020-11-14 | 2020-11-15 | 2020-11-16 | 2020-11-17 | 2020-11-18 | 2020-11-19 | 2020-11-20 | 2020-11-21 | 2020-11-22 | 2020-11-23 | 2020-11-24 | 2020-11-25
Write interim Report | 2020-10-29: Write interim Report
Assemble module #1~#3 together | 2020-10-29: Assemble module #1~#3 together
Debugging | 2020-11-01: Debugging
#4 Module: Panic button Design | 2020-11-04: #4 Module: Panic button Design
# 5 Module: Weather Notifincation Design | 2020-11-10: # 5 Module: Weather Notifincation Design
#6 Module: 'Food' Design | 2020-11-16: #6 Module: 'Food' Design
#7 Module: 'Lifeguard' Design | 2020-11-22: #7 Module: 'Lifeguard' Design

## Nov-Dec
Project timeline
Date of Start : | 2020-11-25
| Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 5
| nov | [5 empty] | dec | dec | [6 empty] | dec | [6 empty] | dec
Date | 2020-11-25 | 2020-11-26 | 2020-11-27 | 2020-11-28 | 2020-11-29 | 2020-11-30 | 2020-12-01 | 2020-12-02 | 2020-12-03 | 2020-12-04 | 2020-12-05 | 2020-12-06 | 2020-12-07 | 2020-12-08 | 2020-12-09 | 2020-12-10 | 2020-12-11 | 2020-12-12 | 2020-12-13 | 2020-12-14 | 2020-12-15 | 2020-12-16 | 2020-12-17 | 2020-12-18 | 2020-12-19 | 2020-12-20 | 2020-12-21 | 2020-12-22
#7 Module: 'Lifeguard' Design | 2020-11-25: #7 Module: 'Lifeguard' Design
Assemble module #4~#7 | 2020-11-27: Assemble module #4~#7
Debugging | 2020-12-01: Debugging
Final Report | 2020-12-03: Final Report